## About this workbook
Activity 5 — Control — Hold the Gain and Hand Over
Certified Lean Six Sigma White Belt (CLSSWB) Training · TGS-2025053210 · Version v5
Scenario: BrewBean Cafe morning rush. Every activity in this course uses the same scenario, so your outputs build into one improvement package.
Tab | Type | What it is for
post-improvement-monitoring | Data (read it) | Post-improvement monitoring — four weeks
control-plan-example | Data (read it) | Control plan — worked example (one row completed)
control-plan-template | Template (fill it in) | Control plan (blank)
sop-and-huddle-template | Template (fill it in) | SOP and daily huddle plan (blank)
one-page-summary-template | Template (fill it in) | One-page DMAIC summary (blank)

## post-improvement-monitoring
Post-improvement monitoring — four weeks
Four weeks of daily average wait times after the pilot was made permanent. The learner uses this in Steps 1-3 to choose the control measure, set the target and write a reaction plan that would have caught the drift.
Week | Day | Date | Avg Wait (min) | Restock Done Before 07:30? | Drinks Remade | Within 8-min Target?
1 | Mon | 2026-06-29 | 6.2 | Yes | 3 | Yes
1 | Tue | 2026-06-30 | 5.9 | Yes | 2 | Yes
1 | Wed | 2026-07-01 | 6.4 | Yes | 3 | Yes
1 | Thu | 2026-07-02 | 6 | Yes | 2 | Yes
1 | Fri | 2026-07-03 | 5.7 | Yes | 2 | Yes
2 | Mon | 2026-07-06 | 6.1 | Yes | 3 | Yes
2 | Tue | 2026-07-07 | 6.6 | Yes | 3 | Yes
2 | Wed | 2026-07-08 | 6.3 | Yes | 2 | Yes
2 | Thu | 2026-07-09 | 6.8 | Yes | 4 | Yes
2 | Fri | 2026-07-10 | 6.2 | Yes | 3 | Yes
3 | Mon | 2026-07-13 | 7.4 | No | 5 | Yes
3 | Tue | 2026-07-14 | 8.9 | No | 6 | No
3 | Wed | 2026-07-15 | 9.6 | No | 6 | No
3 | Thu | 2026-07-16 | 10.2 | No | 7 | No
3 | Fri | 2026-07-17 | 11.1 | No | 8 | No
4 | Mon | 2026-07-20 | 6.5 | Yes | 3 | Yes
4 | Tue | 2026-07-21 | 6.1 | Yes | 2 | Yes
4 | Wed | 2026-07-22 | 5.8 | Yes | 2 | Yes
4 | Thu | 2026-07-23 | 6 | Yes | 3 | Yes
4 | Fri | 2026-07-24 | 5.9 | Yes | 2 | Yes
Note: Week 3 is the drift: a new opening staff member was not shown the restock step, the measure degraded for five days, and nobody noticed until a customer complained on the Friday. Week 4 recovers after the SOP was pinned up and the handover was done properly. This is the whole argument for Control in one dataset — the learner should be able to say exactly which day a reaction plan would have triggered.

## control-plan-example
Control plan — worked example (one row completed)
The control plan format with a single worked row, so the learner can see the level of specificity expected before completing their own in Step 2.
What We Measure | Target | How Often | Who Checks | Where Recorded | Reaction if Off Target
Average customer wait, 07:30-09:00 | <= 8 min (stretch: 5 min) | Daily | Shift supervisor | Board at the barista station | Same day: check the restock was done; if not, do it and tell the opening staff. Two days off target: raise at the huddle and re-brief the whole shift.
Counter milk restocked before 07:15
Drinks remade per morning
Note: Row 1 is the worked example. The learner completes rows 2-4. Note that the reaction column says what to DO, not 'investigate' — a reaction plan that says 'escalate' is not a reaction plan.

## control-plan-template
Control plan (blank)
Steps 1, 2 and 3.
What We Measure | Target | How Often | Who Checks | Where Recorded | Reaction if Off Target

## sop-and-huddle-template
SOP and daily huddle plan (blank)
Steps 5 and 6.
Element | Your entry
SOP title
SOP owner
SOP step 1
SOP step 2
SOP step 3
SOP step 4
SOP step 5
How we know the step was done
Huddle: who attends
Huddle: what time
Huddle: how long
Huddle: what is reviewed
Huddle: who runs it

## one-page-summary-template
One-page DMAIC summary (blank)
Step 7. The whole project on one page.
DMAIC Phase | What we did | What we found / produced
DEFINE
MEASURE
ANALYZE
IMPROVE
CONTROL
Handed over to
Date of handover